## Project_Schedule
| Phase of Development | Activiries to be carried out | Deadline
1 | Analysis and Specification | I analysed social media management systems like Hootsuite, Sprout social, Buffer, Hubspot etc. are paid and they don’t provide the sentimental analysis of the posts. They just track the posts’ analytics. And hence the reputation management can’t be done in those scenarios and we miss out on this important aspect of social media management. After analysis, I decided to go ahead with builing a reputation centric system in Laravel and ReactJS
2 | Designing | For this project, Laravel is used for Backend and ReactJS for frontend. Bootstrap library is used for making layout and since every functionality works on APIs, state management, LocalStorage and a RDBMS is used for Overall System Design
3 | Implementation | I implemented the following features: 1) It is a web Based App developed using Laravel and React JS 2) It uses publicly exposed APIs from Facebook, Linkedin and Twitter to automatically post across these platforms with a single click and gather analytics on post performance
4 | Testing | This was the final phase of my project in which I tested the project on different aspects. All the apis and state management needed to be tested and the final testing was performed on the overall working of the project.

## Record of Activities(Monthwise)
Month | 2020-10-01
| Activities Carried out and Progress Achieved | Remarks Guide
Week1 | This was the ideation phase for our project where I researched about what technology should I use to build the tool.
Week2 | I researched and learned about the php framework laravel
Week3 | I researched and learned about the Javascript framework ReactJS
Week4 | I started with building the login and sign up functionality of the project
Month | 2020-11-01
| Activities Carried out and Progress Achieved | Remarks Guide
Week1 | Complete login and signup functionalities with UI. Also, added api authorization since everything will be done using apis.
Week2 | Researched about how can I retrieve and link various social media sites with my project. Also, learned about oAuth.
Week3 | Started with facebook. Went through its documentation and researched about facebook login.
Week4 | implemented Facebook login and created a DB structure to store user data from facebook
Month | 2020-12-01
| Activities Carried out and Progress Achieved | Remarks Guide
Week1 | Researched about scopes in oAuth and how to ask for them while an external login is going on. Implemented the same for facebook
Week2 | Finished the facebook app review process where I had to explain my project and use cases of their. The review was approved.
Week3 | Started working on LinkedIn login and submitted app review form. Also researched about LinkedIn login using oAuth
Week4 | Completed the LinkedIn login and app review process
Month | 2021-01-01
| Activities Carried out and Progress Achieved | Remarks Guide
Week1 | Started working on the dashboard and retrieve various engagement metrics from facebook and display graphs, widgets etc.
Week2 | Project on hold due to 7th Semester Final Examinations
Week3 | Project on hold due to 7th Semester Final Examinations
Week4 | Implemented Sentimental analysis of the top posts from facebook and Post detail tables.
Month | 2021-02-01
| Activities Carried out and Progress Achieved | Remarks Guide
Week1 | Implemented localStorage concept so that I don't have to do api calls on every page/component load
Week2 | Implemented posting on facebook and created the Ui for the same. The post will be posted on all the pages linked to the facebook account.
Week3 | Implemented content analysis for the content that is about to be posted on the social sites
Week4 | This week I tested the things implementated so far to iron out the bugs. The demo video of this implementation was uploaded in the drive folder.
Month | 2021-03-01
| Activities Carried out and Progress Achieved | Remarks Guide
Week1 | Implemented the dashboard state so that metrics from other social sites can also be visualized
Week2 | Started working on retrieving and visualizing the linkedIn engagement metrics on the dashboard
Week3 | Implemented multimedia posting on Facebook. Now, user would be able to post images along with text in posts.
Week4 | Started working on LinkedIn posting and submitted the form for another app review.
Month | 2021-04-01
| Activities Carried out and Progress Achieved | Remarks Guide
Week1 | Still trying to implement LinkedIn posting. In the mean time, Facebook changed some of their scopes in the login request so changes were required on my end too.
Week2 | This week I created a presentation to showcase our progress, explaing the technologies used and a demo video of the same was also created and was submitted in the drive folder.
Week3 | Finished changes required for facebook login and improved the state management and component reusability in React
Week4 | Finally finished LinkedIn Posting. The user will be able to post images and text on their profile.
Month | 2021-05-01
| Activities Carried out and Progress Achieved | Remarks Guide
Week1 | This week I improved the DB structure, the state management and apis from facebook.
Week2 | Uploaded the code on github. Worked on documentation
Week3 | On hold due to exams
Week4 | This week, I finalized the project and made a video demo explaining the features of the project along with the project report for the final submision.